Time schedule for the various phases of the PT Program

PT/O & M /05/2018-2019: CHEMICAL TESTING - Limestone

Annexure – I

|  |  |  |
| --- | --- | --- |
| S.No. | PT activity | Date by which the activity is to be completed |
| 1 | Dispatching pre notification to prospective participants | 01.04.2019 |
| 2 | Last date for receiving the willingness of prospective participants | 01.05.2019 |
| 3 | Probable date of procuring the PT-items | Already Procured |
| 4 | Expected date of preparing individual PT items for participants and packing the same | 2.05.2019 |
| 5 | Expected date of completing Homogeneity testing | 04.05.2019 to 13.05.2019 |
| 6 | Expected date of completing Stability testing |  |
| 7 | Expected date of dispatch of PT items to the participants | 11.05.2019 |
| 8 | Last date of receipt of PT results from individual participants | 31.05.2019 |
| 9 | Expected date of compiling the PT results and statistical analysis of the same | 07.06.2019 |
| 10 | Expected date of preparation of draft PT scheme report | 11.06.2019 |
| 11 | Expected date of dispatch of final PT scheme report | 18.06.2019 |
| 12 | Last date of receipt of feedback from participants | 22.06.2019 |
| 13 | Expected date of analysis of feedback & taking necessary action | 27.06.2019 |